## Timings
| Month required | Holidays | Release Validation | Post Delivery Modifications | Starts | Ends
Scope 1 | 6.972 | 16 | 3 | 21 | 2026-03-16 | 2026-10-26
Scope 2 | 1.9026 | 8 | 3 | 14 | 2026-10-26 | 2026-12-21
Scope 3 | 1.1906 | 0 | 3 | 7 | 2027-01-04 | 2027-02-14
Scope 4 | 0.61373 | 0 | 3 | 7 | 2027-02-14 | 2027-02-24
Formulas:
Starts = [Ends, row above]
Ends = date(year([Starts]), month([Starts])+[Month required], day([Starts])+[Holidays]+[Release Validation]+[Post Delivery Modifications])

## Scope #1
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS
Scope | 1 | MVP |  |  | 540 | 984 | 603 | 1014
|  | with Custom CRM |  |  | 621 | 1106 | 684 | 1136
|  | with Klaviyo |  |  | 569 | 1047 | 632 | 1077
|  | application architecture |  |  | ~$1200-$3500 pm |  | ~$800-$2500 pm
|  | CRM (custom / klaviyo) |  |  | ~$50-$200 pm |  | ~$1400 pm
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS |  | Comments | Questions
Planning |  |  |  |  | Hours Min Max |  | Hours Min Max
| Planning |  |  |  | 25 | 35 | 25 | 35 | Planning, meetings etc.
Hosting |  |  |  |  | Hours Min Max |  | Hours Min Max
| Database |  |  |  | 10 | 30 | 10 | 30 | Relational DB
| Application | [7 empty] | 118k active users / 105k new users / 3m 11s AVG engagement time / 15k max concurrent
|  | CI/CD |  |  | 40 | 80 | 20 | 30
Testing, Staging
Vimeo
| Monitoring |  |  |  | 1 | 2 | 1 | 2 | CloudWatch / New Relic
| Security |  |  |  | 1 | 2 | 1 | 2 | European CDN
| Monthly costs |  |  |  | ~$1200-$3500 pm |  | ~$800-$2500 pm |  | This also includes scaling with the capability to handle 2 times as many user than 2025.
Admin Site |  |  |  |  | Hours Min Max |  | Hours Min Max
Product Management
Products
|  |  | Grid |  | 1 | 2 | 2 | 4
|  |  | Bulk Actions |  | 1 | 2 | 2 | 3
|  |  | Add / Edit / Remove |  | 2 | 4 | 2 | 4
|  |  | Attributes |  | 4 | 8 | 4 | 8
|  |  | Types |  | 4 | 8 | 4 | 8
Catalogue
|  |  | Categories GTM |  | 6 | 10 | 6 | 8
|  |  | Variants |  | 4 | 8 | 10 | 15
|  |  | Inventory |  | 4 | 8 | 8 | 14
|  |  | Images / Media |  | 3 | 6 | 3 | 6
BISA Specific
|  |  | Gamify Points |  | 2 | 4 | 2 | 4
|  |  | Video Links |  | 1 | 2 | 1 | 2
|  |  | Subscriptioned Price |  | 3 | 6 | 5 | 12
Videos
|  |  | Grid - Library |  | 2 | 4 | 2 | 5
|  |  | Add / Edit / Remove |  | 4 | 8 | 4 | 8
|  |  | DRM / Access Control |  | 6 | 12 | 12 | 20 | Digital Rights Management
|  |  | Progress Tracking |  | 10 | 15 | 10 | 15
|  |  | Playlists / Series |  | 10 | 15 | 10 | 15
|  |  | Subscription Mapping |  | 15 | 20 | 8 | 10
|  |  | Analytics |  | 4 | 8 | 8 | 15
Order Fulfillment
Orders
|  |  | Grid |  | 1 | 3 | 2 | 4
|  |  | Add / Edit / Remove |  | 1 | 3 | 2 | 3
|  |  | Status |  | 1 | 2 | 1 | 1
Invoice
|  |  |  | Szamlazz.hu | 6 | 10 | 6 | 10
Shipping
Carrier
|  |  |  | Foxpost | 2 | 2 | 3 | 3
|  |  |  | DPD | 2 | 3 | 3 | 3
|  |  |  | MPL | 2 | 4 | 3 | 4
Payments
|  |  | Subscriptions |  | 16 | 24 | 16 | 24
Notifications
|  | Fulfillment reports |  |  | 3 | 6 | 5 | 6
|  | Stock alerts |  |  | 1 | 1 | 2 | 4
|  | Shipment notifications |  |  | 1 | 2 | 1 | 3
User Management
|  | Add/Edit/Delete |  |  | 2 | 5 | 5 | 10
|  | User impersonation |  |  | 2 | 4 | 6 | 10
Gamification
Triggers
|  |  | Profile |  | 1 | 2 | 1 | 2
|  |  | Purchase |  | 1 | 2 | 1 | 2
|  |  | Subscription |  | 1 | 2 | 1 | 2
|  |  | Video |  | 1 | 2 | 1 | 2
|  |  | Event |  | 1 | 2 | 1 | 2
|  |  | Streak |  | 1 | 2 | 1 | 2
Payment Integrations
|  | Stripe |  |  | 5 | 10 | 10 | 18
Admin Users
|  | Add/Edit/Delete |  |  | 10 | 20 | 10 | 20
Public Site |  |  |  |  | Hours Min Max |  | Hours Min Max
| PWA |  |  |  | 0 | 0 | 5 | 8 | progressive web application
Miscellaneous
|  | Blog |  |  | 12 | 24 | 10 | 18
|  | Introduction |  |  | 2 | 3 | 2 | 3
|  | Carousel |  |  | 2 | 3 | 2 | 3
|  | FAQ |  |  | 2 | 3 | 2 | 3
|  | Contact |  |  | 2 | 3 | 2 | 3
|  | Privacy & Compliance |  |  | 1 | 2 | 1 | 2
User
|  | Authentication |  |  | 1 | 2 | 4 | 6
|  |  | Onboarding |  | 6 | 8 | 8 | 10
|  |  | User impersonation |  | 1 | 3 | 1 | 4
Social logins
|  |  |  | email + pw | 1 | 3 | 1 | 3
|  |  |  | apple | 3 | 8 | 8 | 10
|  |  |  | google | 2 | 6 | 6 | 10
|  | Profile |  |  | 3 | 8 | 3 | 8
|  | Onboarding |  |  | 5 | 6 | 5 | 6
Catalog
|  | Products (including events) |  |  | 10 | 25 | 10 | 25
|  | Videos |  |  | 10 | 12 | 8 | 10
Checkout
|  | Cart |  |  | 8 | 15 | 12 | 18
|  | Guest |  |  | 10 | 20 | 15 | 20
|  | Payment |  |  | 5 | 10 | 5 | 10
|  | Coupon code |  |  | 2 | 6 | 1 | 5
|  | Shipping |  |  | 2 | 5 | 2 | 5
Video Player
|  | Embed |  |  | 2 | 4 | 2 | 4
|  | Progress Tracking |  |  | 2 | 2 | 2 | 2
Gamification
|  | Triggers |  |  | 1 | 2 | 1 | 2
|  | Rewards |  |  | 3 | 4 | 3 | 4
SEO
|  | Server Side Rendering |  |  | 0 | 0 | 0 | 0
|  | Search Engine Optimization |  |  | 0 | 0 | 0 | 0
UI |  |  |  |  | Hours Min Max |  | Hours Min Max
| Public FrontEnd |  |  |  | 60 | 100 | 60 | 100
CRMs
Klaviyo
|  | Development time |  |  | 29 - 63
|  | Klaviyo |  |  | ~$1400 pm
Custom CRM + SendGrid
|  | Development time |  |  | 81 - 122
|  | SendGrid |  |  | ~$50-$200 pm
CRM Metrics |  |  |  |  | Custom CRM |  | Klaviyo |  | Comments | Questions
[5 empty] | Hours Min Max |  | Hours Min Max
| Metrics |  |  |  | 81 | 122 | 29 | 63
|  | Subscription status (subscription_status) |  |  | 8 | 16 | 2 | 6
|  | Subscription start date / days since subscription (subscription_start_date, subscription_days_active) |  |  | 8 | 12 | 2 | 4
|  | Monthly Recurring Revenue, churn (mrr, revenue_churn, is_churned) |  |  | 16 | 24 | 4 | 8
|  | Customer Lifetime Value (customer_ltv) |  |  | 8 | 12 | 2 | 12
|  | Order count by type (order_count_total, order_count_gear, order_count_video, order_count_event) |  |  | 12 | 16 | 3 | 8
|  | Repeat buyer flag (is_repeat_buyer) |  |  | 6 | 10 | 3 | 5
|  | Days since last order (days_since_last_order) |  |  | 8 | 12 | 4 | 6
|  | Refund ratio / count (refund_count, refund_ratio) |  |  | 12 | 16 | 6 | 10
|  | Site Performance |  |  | 3 | 4 | 3 | 4

## Scope #2
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS
Scope | 2 | User Engagement |  |  | 113 | 188 | 127 | 210
|  | with Custom CRM |  |  | 177 | 288 | 191 | 310
|  | with Klaviyo |  |  | 146 | 241 | 160 | 263
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS |  | Comments | Questions
Admin Site |  |  |  |  | Hours Min Max |  | Hours Min Max
Product Management
Catalogue
|  |  | Upsell |  | 2 | 4 | 3 | 5
Videos
Gamification
|  |  | Badges |  | 2 | 4 | 3 | 5
Order Fulfillment
Payments / Refunds
|  |  | Failed Payment Retry |  | 8 | 15 | 8 | 15
Gamification & Entitlements
Rewards / Badges
|  |  | Grid - Library |  | 1 | 2 | 1 | 2
|  |  | Add / Edit / Remove / Upload |  | 5 | 8 | 5 | 8
|  |  | Logic Builder |  | 16 | 24 | 16 | 24
Entitlements
|  |  | List |  | 5 | 8 | 5 | 8
|  |  | Add / Edit / Remove |  | 5 | 8 | 5 | 8
|  |  | Discount |  | 5 | 8 | 5 | 8
|  |  | Benefit |  | 5 | 8 | 5 | 8
|  |  | Logic Builder |  | 8 | 10 | 8 | 10
Public Site
User
Advanced Profile
|  |  | Share Badge |  | 8 | 10 | 8 | 10
Gamification
|  |  |  | Badges | 4 | 8 | 4 | 8
|  |  |  | Onboarding+ | 4 | 8 | 4 | 8
Social logins
|  |  |  | facebook | 1 | 1 | 1 | 1
|  |  |  | instagram | 1 | 3 | 6 | 12
|  |  |  | facebook | 2 | 5 | 6 | 12
|  |  |  | tiktok | 3 | 8 | 6 | 12
Entitlements
|  |  |  | Feature #1 | 4 | 8 | 4 | 8
|  |  |  | Feature #2 | 4 | 8 | 4 | 8
UI
| Public FrontEnd |  |  |  | 20 | 30 | 20 | 30
CRMs
Klaviyo
|  | Development time |  |  | 33 - 53
Custom CRM + SendGrid
|  | Development time |  |  | 64 - 100
CRM Metrics |  |  |  |  | Custom CRM |  | Klaviyo |  | Comments | Questions
[5 empty] | Hours Min Max |  | Hours Min Max
| Metrics |  |  |  | 64 | 100 | 33 | 53
|  | Badges and level (badge_list, badge_count, gamification_level) |  |  | 12 | 20 | 4 | 8
|  | Gamification activity flag (is_gamified_active) |  |  | 8 | 12 | 4 | 6
|  | Fitness goals (fitness_goal) |  |  | 6 | 10 | 3 | 5
|  | Fitness level (fitness_level) |  |  | 6 | 10 | 3 | 5
|  | Days since last login (days_since_last_login, last_login_at) |  |  | 8 | 12 | 4 | 6
|  | Video engagement 30d (video_minutes_30d, video_views_30d) |  |  | 10 | 16 | 6 | 8
|  | Program progress status (program_X_status) |  |  | 8 | 12 | 6 | 10
|  | Binge viewer flag (is_binge_viewer) |  |  | 6 | 8 | 3 | 5

## Scope #3
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS
Scope | 3 | Full fledged Gamification |  |  | 66 | 106 | 66 | 106
|  | with Custom CRM |  |  | 124 | 194 | 124 | 194
|  | with Klaviyo |  |  | 91 | 145 | 91 | 145
[5 empty] | Magento2 / Hyva |  | Vendure / NextJS |  | Comments | Questions
Admin Site |  |  |  |  | Hours Min Max |  | Hours Min Max
Gamification & Entitlements
Rewards / Badges
|  |  | Logic Builder+ |  | 16 | 24 | 16 | 24
Entitlements
|  |  | Discount+ |  | 5 | 8 | 5 | 8
|  |  | Benefit+ |  | 5 | 8 | 5 | 8
|  |  | Logic Builder+ |  | 8 | 10 | 8 | 10
Public Site
User
Advanced Profile
Social logins
|  |  |  | QR TV | 8 | 16 | 8 | 16
Entitlements
|  |  |  | Feature #3 | 4 | 8 | 4 | 8
|  |  |  | Feature #4 | 4 | 8 | 4 | 8
UI
| Public FrontEnd |  |  |  | 16 | 24 | 16 | 24
CRMs
Klaviyo
|  | Development time |  |  | 25 - 39
Custom CRM + SendGrid
|  | Development time |  |  | 58 - 88
CRM Metrics |  |  |  |  | Custom CRM |  | Klaviyo |  | Comments | Questions
[5 empty] | Hours Min Max |  | Hours Min Max
| Metrics |  |  |  | 58 | 88 | 25 | 39
|  | Preferred device (preferred_device) |  |  | 6 | 10 | 3 | 5
|  | Content interests / favorite categories (interests, pl. tag‑lista) |  |  | 12 | 18 | 6 | 10
|  | Achievement impact score/flag (achievement_impact_score, high_achievement_impact) |  |  | 16 | 24 | 8 | 12
|  | Reward / coupon redemption flag (reward_redeemed, reward_redemption_count) |  |  | 8 | 12 | 4 | 6
|  | Segment export (min orders) (min_orders_segment_export) |  |  | 16 | 24 | 4 | 6

## Scope #4
Vendure / NextJS
Scope | 4 | Moonshot | 70 | 100
|  |  | Vendure / NextJS |  | Comments | Questions
AI RAG |  |  | Hours Min Max
Tudásbázis
|  | Tudásbázis | 50 | 70
Maintenance
| Maintenance |  | 20 | 30

## Quote Mine C
BSS Percent |  | 15%
[6 empty] | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15%
SCOPE #1 | [5 empty] | 5000 | 7518.797 | 8496.2406 | 8943.4112 | 9995.5772 | 6500 | 9774.4361 | 11045.1128 | 11626.4345 | 12994.2503 | 7400 | 11127.8196 | 12574.4361 | 13236.2485 | 14793.4542 | 8000 | 12030.0752 | 13593.985 | 14309.4579 | 15992.9235 | 9500 | 14285.7143 | 16142.8571 | 16992.4812 | 18991.5966
|  | HOURS | DAYS | WEEKS | MONTHS | 814687.5 | 1225093.985 | 1384356.203 | 1457217.056 | 1628654.356 | 1059093.75 | 1592622.18 | 1799663.064 | 1894382.173 | 2117250.663 | 1205737.5 | 1813139.098 | 2048847.18 | 2156681.243 | 2410408.448 | 1303500 | 1960150.376 | 2214969.925 | 2331547.289 | 2605846.97 | 1547906.25 | 2327678.571 | 2630276.786 | 2768712.406 | 3094443.277
Magento2 / Hyva (max) | Total | 1106 | 147.4667 | 29.4933 | 6.7879 | 5530000 | 8315789.474 | 9396842.105 | 9891412.742 | 11055108.36 | 7189000 | 10810526.32 | 12215894.74 | 12858836.57 | 14371640.87 | 8184400 | 12307368.42 | 13907326.32 | 14639290.86 | 16361560.37 | 8848000 | 13305263.16 | 15034947.37 | 15826260.39 | 17688173.37 | 10507000 | 15800000 | 17854000 | 18793684.21 | 21004705.88
Vendure / NextJs (max) | Total | 1136 | 151.4667 | 30.2933 | 6.972 | 5680000 | 8541353.383 | 9651729.323 | 10159715.08 | 11354975.67 | 7384000 | 11103759.4 | 12547248.12 | 13207629.6 | 14761468.38 | 8406400 | 12641203.01 | 14284559.4 | 15036378.31 | 16805364 | 9088000 | 13666165.41 | 15442766.92 | 16255544.12 | 18167961.08 | 10792000 | 16228571.43 | 18338285.71 | 19303458.65 | 21574453.78
[6 empty] | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15%
SCOPE #2 | [5 empty] | 5000 | 7518.797 | 8496.2406 | 8943.4112 | 9995.5772 | 6500 | 9774.4361 | 11045.1128 | 11626.4345 | 12994.2503 | 7250 | 10902.2556 | 12319.5489 | 12967.9462 | 14493.5869 | 8000 | 12030.0752 | 13593.985 | 14309.4579 | 15992.9235 | 9500 | 14285.7143 | 16142.8571 | 16992.4812 | 18991.5966
|  | HOURS | DAYS | WEEKS | MONTHS | 212142.8571 | 319011.8153 | 360483.3512 | 379456.1592 | 424098.0603 | 275785.7143 | 414715.3598 | 468628.3566 | 493293.007 | 551327.4784 | 307607.1429 | 462567.1321 | 522700.8593 | 550211.4308 | 614942.1874 | 339428.5714 | 510418.9044 | 576773.362 | 607129.8547 | 678556.8964 | 403071.4286 | 606122.449 | 684918.3673 | 720966.7025 | 805786.3145
Magento2 / Hyva (max) | Total | 288 | 38.4 | 7.68 | 1.7675 | 1440000 | 2165413.534 | 2446917.293 | 2575702.414 | 2878726.227 | 1872000 | 2815037.594 | 3180992.481 | 3348413.138 | 3742344.096 | 2088000 | 3139849.624 | 3548030.075 | 3734768.5 | 4174153.03 | 2304000 | 3464661.654 | 3915067.669 | 4121123.862 | 4605961.964 | 2736000 | 4114285.714 | 4649142.857 | 4893834.586 | 5469579.832
Vendure / NextJs (max) | Total | 310 | 41.3333 | 8.2667 | 1.9026 | 1550000 | 2330827.068 | 2633834.586 | 2772457.459 | 3098628.925 | 2015000 | 3030075.188 | 3423984.962 | 3604194.697 | 4028217.603 | 2247500 | 3379699.248 | 3819060.15 | 4020063.316 | 4493011.942 | 2480000 | 3729323.308 | 4214135.338 | 4435931.935 | 4957806.28 | 2945000 | 4428571.429 | 5004285.714 | 5267669.173 | 5887394.958
[6 empty] | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15%
SCOPE #3 | [5 empty] | 5000 | 7518.797 | 8496.2406 | 8943.4112 | 9995.5772 | 6500 | 9774.4361 | 11045.1128 | 11626.4345 | 12994.2503 | 7250 | 10902.2556 | 12319.5489 | 12967.9462 | 14493.5869 | 8000 | 12030.0752 | 13593.985 | 14309.4579 | 15992.9235 | 9500 | 14285.7143 | 16142.8571 | 16992.4812 | 18991.5966
|  | HOURS | DAYS | WEEKS | MONTHS | 142901.7857 | 214889.9033 | 242825.5908 | 255605.885 | 285677.1656 | 185772.3214 | 279356.8743 | 315673.268 | 332287.6505 | 371380.3153 | 207207.5893 | 311590.3598 | 352097.1066 | 370628.5333 | 414231.8901 | 228642.8571 | 343823.8453 | 388520.9452 | 408969.416 | 457083.465 | 271513.3929 | 408290.8163 | 461368.6224 | 485651.1815 | 542786.6146
Magento2 / Hyva (max) | Total | 194 | 25.8667 | 5.1733 | 1.1906 | 970000 | 1458646.617 | 1648270.677 | 1735021.765 | 1939141.973 | 1261000 | 1896240.602 | 2142751.88 | 2255528.294 | 2520884.564 | 1406500 | 2115037.594 | 2389992.481 | 2515781.559 | 2811755.86 | 1552000 | 2333834.586 | 2637233.083 | 2776034.824 | 3102627.156 | 1843000 | 2771428.571 | 3131714.286 | 3296541.353 | 3684369.748
Vendure / NextJs (max) | Total | 194 | 25.8667 | 5.1733 | 1.1906 | 970000 | 1458646.617 | 1648270.677 | 1735021.765 | 1939141.973 | 1261000 | 1896240.602 | 2142751.88 | 2255528.294 | 2520884.564 | 1406500 | 2115037.594 | 2389992.481 | 2515781.559 | 2811755.86 | 1552000 | 2333834.586 | 2637233.083 | 2776034.824 | 3102627.156 | 1843000 | 2771428.571 | 3131714.286 | 3296541.353 | 3684369.748
[6 empty] | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15% | netto | brutto | ossz.kolts | 5% | 15%
SCOPE #4 | [5 empty] | 5000 | 7518.797 | 8496.2406 | 8943.4112 | 9995.5772 | 6500 | 9774.4361 | 11045.1128 | 11626.4345 | 12994.2503 | 7250 | 10902.2556 | 12319.5489 | 12967.9462 | 14493.5869 | 8000 | 12030.0752 | 13593.985 | 14309.4579 | 15992.9235 | 12000 | 18045.1128 | 20390.9774 | 21464.1868 | 23989.3852
|  | HOURS | DAYS | WEEKS | MONTHS | 73660.7143 | 110767.9914 | 125167.8303 | 131755.6108 | 147256.2709 | 95758.9286 | 143998.3888 | 162718.1794 | 171282.2941 | 191433.1522 | 106808.0357 | 160613.5875 | 181493.3539 | 191045.6357 | 213521.5928 | 117857.1429 | 177228.7863 | 200268.5285 | 210808.9773 | 235610.0335 | 176785.7143 | 265843.1794 | 300402.7927 | 316213.466 | 353415.0502
Magento2 / Hyva (max) | Total | 100 | 13.3333 | 2.6667 | 0.61373 | 500000 | 751879.6992 | 849624.0602 | 894341.1159 | 999557.7178 | 650000 | 977443.609 | 1104511.278 | 1162643.451 | 1299425.033 | 725000 | 1090225.564 | 1231954.887 | 1296794.618 | 1449358.691 | 800000 | 1203007.519 | 1359398.496 | 1430945.786 | 1599292.349 | 1200000 | 1804511.278 | 2039097.744 | 2146418.678 | 2398938.523
Vendure / NextJs (max) | Total | 100 | 13.3333 | 2.6667 | 0.61373 | 500000 | 751879.6992 | 849624.0602 | 894341.1159 | 999557.7178 | 650000 | 977443.609 | 1104511.278 | 1162643.451 | 1299425.033 | 725000 | 1090225.564 | 1231954.887 | 1296794.618 | 1449358.691 | 800000 | 1203007.519 | 1359398.496 | 1430945.786 | 1599292.349 | 1200000 | 1804511.278 | 2039097.744 | 2146418.678 | 2398938.523

## Questions
Mi kerul az MVP-be?
Badge / Reward az mindig custom kod kellene legyen szerintem, jol gondolom? Ahogy kb minden gamification logika
Gamification resze az MVP-nek? Sokszunisege miatt kellene leiras hogy pontosan milyenek az indulok
Mit szeretnenek a LearnDash logikabol viszontlatni?
Termek kategoria rendszer bonyolultsaga? Fa / ala fole rendeltsegek?
Milyen metricsek kellenenek az MVP-hez?
Beyond The Motion kivaltasa cel volna? Gondolnam...
Mennyi latogato eri havonta az oldalt?
Ez egy nagyobb UX scope aminek a reszletes rajzaival tartozom, de a videok megtekintettseget es a vasarlasi szokasokat osszefogo Profile komponensben kapna helyet. Ami fontos, hogy challengeket is szeretne tudni Aniko inditani, melyek javadalmazhatoak badge-dzsel es/vagy kuponkoddal.
Nemelyik challenge merheto programatikusan (eg. vasarolj videot es hozza tartozo eszkozt; nezz vegig egy proramot) nemelyik egyelore nem (eg. tornazz legalabb haromszor a heten). Utobbiakat manualisan szeretnenk tudni odaitelni, de a programatikusan odaiteltek vagy epp elmulasztottak orvoslatahoz is hasznos a manualis felulbiralas.
Igen, ezzel tartozom. Upfront dokumentalas helyett egy szamotokra fontos kerdezes menten folytatott wireframing sessiont tartanek a leghatekonyabbnak.
mi volna a cel igazabol? mi zajlik a hatterben...
Ebben nem vagyok biztos. Meg kell kerdeznem @erika.komaromi@gmail.com -t , hogy FluentCRM honnan szerzi az adatokat.
Ezeken mind segített volna ha Erika megejti multheten a körbemutogató meetinget.
hány contact / havi email volume
mennyire fontos a „mindig 1 helyen látom a user teljes történetét” vs. „inkább marketing automation legyen erős”,
mi az mvp complexitasban?
magyar megoldas a CDN/-re | nincs
gtm-bol tag-ek vissza vagy ok irjak a tag-eket amik gtm-be is bemennek
labda vissza crm-re van e favoritjuk stb, ketto popularisat kuldeni nekik azert |  | klaviyo, customer.io, bento, HubSpot Marketing Hub + CRM, Braze
gamification logika megoldasi javaslat utanaznezni prezentalni nekik? |  | kuldott gtm tag-ek nyoman badge keszito felulet adminba - lenyegeben kettos kuldes, adatbazisba is, adminon szabadon osszeallithato
maintenance -ra oradijas havi X oraszamu rendelkezesre allas?

## metrics
Metrika (HU) | Metrika – angol név (javaslat) | Saját CRM – plusz fejlesztés | Idő (Saját, óra) | Klaviyo – plusz fejlesztés (attribútum + segment) | Idő (Klaviyo, óra)
Előfizetés státusz (aktív / lemondott) | Subscription status (subscription_status) | Létező subscription mezők felhozatala listába, státusz‑filter, egyszerű count‑kártya | 8–16 | Subscription státusz mező API‑sync (webhook handler + 1–2 segment) | 4–8
Előfizetés kezdete / „előfizetett X napja” | Subscription start date / days since subscription (subscription_start_date, subscription_days_active) | Oszlop + dátumszűrő (UI), egyszerű „days_since_start” kalkuláció | 8–12 | subscription_start_date kiküldése + date‑alapú segmentek beállítása | 4–6
MRR + churn áttekintés | Monthly Recurring Revenue, churn (mrr, revenue_churn, is_churned) | Egyszerű MRR‑aggregáció meglévő billing táblákból + 1 grafikon + churn count | 16–24 | Backend MRR/churn aggregátok küldése 1‑2 mezőben + segment high/low MRR‑re | 8–12
Lifetime érték (összbevétel userenként) | Customer Lifetime Value (customer_ltv) | LTV mező kiszámítása meglévő order táblából + oszlop + szűrő | 8–12 | LTV összeg küldése attribute‑ként + segment (high LTV) | 4–6
Rendelésszám userenként, terméktípusonként | Order count by type (order_count_total, order_count_gear, order_count_video, order_count_event) | Count + egyszerű típus szerinti aggregáció, oszlop + filter a listában | 12–16 | 2–3 aggregált mező sync + segment | 6–10
Ismétlődő vásárló flag | Repeat buyer flag (is_repeat_buyer) | Egyszerű szabály (>=2 order) + flag mező + filter | 6–10 | Flag számítása backendben + attribute + segment | 3–5
„Nem vásárolt X napja” | Days since last order (days_since_last_order) | Last_order_date mező + listaszűrő (dátum intervallum) | 8–12 | last_order_date attribute + relative time segment („has not ordered in 60 days”) | 4–6
Refund / karbantartási jelző | Refund ratio / count (refund_count, refund_ratio) | Refund count / ratio mező + filter, nem full riport | 12–16 | Refund count/ratio attribute + segment (pl. high refund) | 6–10
Gamification badge‑ek, szintek | Badges and level (badge_list, badge_count, gamification_level) | Létező badge adatok megjelenítése (chip‑ek / count) + filter badge típusa szerint | 16–24 | badge list/count mezők sync + segmentek (has badge X) | 8–12
„Gamificationben aktív” flag | Gamification activity flag (is_gamified_active) | Létező eventekből egyszerű utolsó‑aktivitás alapú flag + filter | 8–12 | Flag számítása backendben + attribute + segment | 4–6
Profil célok | Fitness goals (fitness_goal) | Oszlop + szűrő az admin listában | 6–10 | Mező sync + goal‑alapú segmentek | 3–5
Edzettségi szint | Fitness level (fitness_level) | Oszlop + szűrő | 6–10 | Mező sync + level‑alapú segmentek | 3–5
„X napja nem lépett be” | Days since last login (days_since_last_login, last_login_at) | Last_login mező kijelzés + relatív dátum‑filter UI | 8–12 | last_login_at attribute + „has not logged in in X days” segment | 4–6
Videó‑megtekintés (30 nap, perc / darab) | Video engagement 30d (video_minutes_30d, video_views_30d) | Már számolt watch time/view count felhozatala oszlopba + 1 grafikon | 16–24 | Attribútumok sync + heavy/low viewer segmentek | 8–12
Program státusz (elkezdve / 50% / 100%) | Program progress status (program_X_status) | Egyszerű státusz mező kijelzés + filter (pl. dropdown) | 12–18 | program_X_status mező sync + segment (completed / in progress) | 6–10
„Binge viewer” flag | Binge viewer flag (is_binge_viewer) | Flag oszlop + filter | 6–8 | Flag attribute sync + segment | 3–5
Eszköz‑preferencia | Preferred device (preferred_device) | Már aggregált mező kijelzése + filter | 6–10 | preferred_device attribute + device‑alapú segmentek | 3–5
Kedvenc kategóriák / érdeklődés | Content interests / favorite categories (interests, pl. tag‑lista) | Létező interest tag‑ek vizuális megjelenítése + tag‑filter | 12–18 | interests attribute sync + interest‑alapú segmentek | 6–10
Achievement‑hatás score/flag | Achievement impact score/flag (achievement_impact_score, high_achievement_impact) | Score/flag mező kijelzés + filter + 1 grafikon | 16–24 | Score/flag attribute sync + 1–2 segment | 8–12
Reward / kupon beváltás flag | Reward / coupon redemption flag (reward_redeemed, reward_redemption_count) | Mező kijelzése (redeemed / not) + filter | 8–12 | Attribute sync + segment (redeemed vs not) | 4–6
Exportálható szegmensek (min. rendelés + email) | Segment export (min orders) (min_orders_segment_export) | Egyszerű szűrőkombo + „export CSV” gomb a meglévő listára | 16–24 | Klaviyó built‑in export: csak segment definíció + export workflow | 4–6

## planning
planning
db structure

## Magento2 vs Vendure
Magento2/Hyva vs Vendure/NextJs
Vendur jobban scale-elhető, custom fejlesztések hatékonyabban.
MVP lassabb, tobb egyedi kodot igenyel. Becslesek szerint ez olyan kb 25% plusz.
Magento MVP-re lenyegesen gyorsabb (ha valaki tapasztalt benne), kesobb valik verejtekesse.
Hyva template kb 400k huf egyszeri osszeg de magentot ertekesito cegek tobbnyire ezzel adjak termekeiket.
Frontend munka hatekonyabb modern technologiakkal es nullarol irva, mint a regit atalakítani.
SEO
Hyva: |  | Vendure / NextJs:
Lightning Speed (SSR + minimal JS) | Lightning Speed | Next.js SSR/SSG/ISR; GraphQL caching → 95+ Lighthouse. | Native; Vercel/Netlify free perf. Better for global.
Semantic HTML5 | Semantic HTML5 | React components w/ ARIA/Headless UI → crawlable. | Default; add next-seo plugin.
Mobile-First | Mobile-First | Tailwind in Next.js starter → responsive/PWA. | Identical.
Lazy Loading | Lazy Loading | next/image + React.lazy → auto. | Built-in.
Meta/Structured Data | Meta/Structured | next/head + @schema-dts → JSON-LD. | 1h setup.
No Render-Blocking | No Render-Blocking | Next.js optimizes CSS/JS → minimal bundle. | Superior (code-split).
CI/CD Testing / Staging / Live
Aspect | Vendure/Next.js | Magento/Hyvä | Notes
Pipeline Speed | Fast (Node/JS) | Slower (PHP/SCD 10–30min) | Hyvä speeds frontend.
Testing | Vitest + Vendure E2E (easy) | Playwright Hyvä + PHPUnit (robust) | Both cover UI/API.
Staging Cost | Low (Vercel free tier) | Medium (Docker infra) | Both env vars/secrets.
Prod Deploy | Auto Vercel | Manual approval + rollback | Git tags best.
Maintenance | Low | Medium (Composer updates) | Dependabot both.
Hosting costs
Vendure / Nextjs | Component | Cost | Notes
| Vercel Pro+ | $500–1,500 | 30k concurrent; bandwidth heavy.
| Supabase | $150–400 | 236k users; replicas.
| Redis/CDN | $100–300 | Sessions/cache.
| Monitoring | $50–200 | Sentry/Datadog.
~$800-$2500
Magento2 / Hyva | Component | Cost | Notes
| ECS (10x m6i.large) | $600–1,500 | Auto-scale spikes.
| Aurora DB | $300–800 | Read replicas.
| Redis/Varnish | $150–400 | Full-page cache.
| CDN/S3 | $100–300 | Gear/videos.
| Monitoring | $50–200 | CloudWatch.
~$1200-$3500
Ezek a modern, nem-PHP alapú alternatívák gyorsabb fejlesztést, jobb skálázást és könnyebb gamification/AI integrációt kínálnak a BISA MVP-hez (katalógus, Stripe/Foxpost, CRM, PWA) – headless/composable architektúrával, ahol frontend/backend külön skáláz.
Top 3 alternatíva (fitness/gamified e-comm-ra optimalizálva)
|  |  |  | Stack | Mi ez? | Miért jobb, mint Magento+Hyvä? | BISA MVP implementáció
|  |  |  | Shopify Plus + Hydrogen (React/Next.js) | Shopify backend (GraphQL API) + Hydrogen frontend (React 19, Remix). | JS/TS full-stack, 5x gyorsabb deploy (Vercel/Oxygen), natív subscription/bundles; nincs PHP legacy/maintain költség. Havi ~2000 EUR, de korlátlan scale.
|  |  |  | ​ | Katalógus: Shopify Products API; checkout: Stripe checkout; PLP: Hydrogen filtered collections; PWA: beépített.
|  |  |  | commercetools + Next.js/Vue storefront | API-first composable backend (JavaScript SDK) + custom React frontend. | Teljes moduláris (webshop/gamification külön service), real-time achievement-ek (WebSockets), EU GDPR-native; versenytársaknál 2x gyorsabb personalization.
Katalógus: custom product types (gear/video/event); fizetés: Stripe plugin; CRM: Zapier/Make.com integráció; landing: Vercel deploy 2 hét alatt.
|  |  |  | Vendure (Node.js/TS GraphQL) + Next.js | Open-source headless backend (TypeScript) + modern frontend. | Teljesen ingyenes, developer-friendly (Admin UI gamification configra), könnyű AI coach hookup (Node ML); gyorsabb, mint PHP bármi.
|  |  |  | ​ | Katalógus: GraphQL schema (virtuális termékek); checkout: Stripe plugin; PWA: Next.js PWA module; mobil-first Tailwind.

## Q 11022026
MVP tartalmat pontosan meghatarozni |  |  |  |  | 6 | 10
Fazisok meghatarozasa |  |  |  |  | 1008 | 1680
UI becslés? mvp ui nélkül?
óradíj |  |  | 6 | 10
orabecsles
Nagyjaboli ar meghatarozasa
timeline az iteracioknak
Kozos mukodes meghatarozasa |  |  |  | 50-15% kozott nem fizetik ki az alvallalkozonak
Gergo - Cyber Security DevOps PHD tanit Obudai Egyetemen
Vera - Project Management es SQL adatbazis kezeles stb
Laci - tud segiteni de le van kotve / nyelvesz
Krisztian - verinformatikus / denever
sendgrid vs fluentcrm - van elofizetesuk es kvotajuk is
cloud code?? | ceges szinten elofizetni
meeting | delelott | 10:00

## Quote Mine (hidden)
Planning |  |  | Magento2 / Hyva |  |  | Vendure / NextJS |  |  |  | MVP | MVP | Month | MVP | MVP | Month
|  |  | Min | Max |  | Min | Max |  |  | 391 | 714 | 4.382 | 414 | 705 | 4.3268
SUMS |  | MVP | 25 | 35 |  | 25 | 35 |  |  | #1 | #1 |  | #1 | #1
|  | #1 | 0 | 0 |  | 0 | 0 |  |  | 29 | 58 | 0.35596 | 47 | 89 | 0.54622
|  | #2 | 0 | 0 |  | 0 | 0 |  |  | #2 | #2 |  | #2 | #2
|  | TBD | 0 | 0 |  | 0 | 0 |  |  | 20 | 36 | 0.22094 | 20 | 36 | 0.22094
|  | Total | 25 | 35 |  | 25 | 35 |  |  | TBD | TBD |  | TBD | TBD
[10 empty] | 12 | 25 | 0.15343 | 19 | 40 | 0.24549
Hosting |  |  | Magento2 / Hyva |  |  | Vendure / NextJS
|  |  | Min | Max |  | Min | Max
SUMS |  | MVP | 52 | 114 |  | 32 | 64
|  | #1 | 0 | 0 |  | 0 | 0
|  | #2 | 0 | 0 |  | 0 | 0
|  | TBD | 0 | 0 |  | 0 | 0
|  | Total | 52 | 114 |  | 32 | 64
Admin Site |  |  | Magento2 / Hyva |  |  | Vendure / NextJS
|  |  | Min | Max |  | Min | Max
SUMS |  | MVP | 146 | 264 |  | 171 | 299
|  | #1 | 21 | 39 |  | 27 | 50
|  | #2 | 10 | 16 |  | 10 | 16
|  | TBD | 12 | 25 |  | 19 | 40
|  | Total | 189 | 344 |  | 227 | 405
Public Site |  |  | Magento2 / Hyva |  |  | Vendure / NextJS
|  |  | Min | Max |  | Min | Max
SUMS |  | MVP | 108 | 201 |  | 126 | 207
|  | #1 | 8 | 19 |  | 20 | 39
|  | #2 | 10 | 20 |  | 10 | 20
|  | TBD | 0 | 0 |  | 0 | 0
|  | Total | 126 | 240 |  | 156 | 266
UI |  |  | Magento2 / Hyva |  |  | Vendure / NextJS
|  |  | Min | Max |  | Min | Max
SUMS |  | MVP | 60 | 100 |  | 60 | 100
|  | #1 | 0 | 0 |  | 0 | 0
|  | #2 | 0 | 0 |  | 0 | 0
|  | TBD | 0 | 0 |  | 0 | 0
|  | Total | 60 | 100 |  | 60 | 100
ESTIMATED |  | HOURS | 452 | 833 |  | 500 | 870
|  | DAYS | 60.2667 | 111.0667 |  | 66.6667 | 116
|  | WEEKS | 12.0533 | 22.2133 |  | 13.3333 | 23.2
|  | MONTHS | 2.7741 | 5.1124 |  | 3.0687 | 5.3395
[6 empty] | 18% | 11397.3102 |  |  | 14816.5033 |  |  | 16412.1267 |  |  | 18235.6964 |  |  | 21654.8894
[6 empty] | 53.5% | 9345.7944 |  |  | 12149.5327 |  |  | 13457.9439 |  |  | 14953.271 |  |  | 17757.0094
[7 empty] | 5000 |  |  | 6500 |  |  | 7200 |  |  | 8000 |  |  | 9500
|  |  | HOURS | DAYS | WEEKS | MONTHS | 814687.5 | 1522780.374 | 1857049.236 | 1059093.75 | 1979614.486 | 2414164.007 | 1173150 | 2192803.738 | 2674150.9 | 1303500 | 2436448.598 | 2971278.778 | 1547906.25 | 2893282.71 | 3528393.549
ESTIMATED | Magento2 / Hyva MIN | MVP | 29 | 3.8667 | 0.77333 | 0.17798 | 145000 | 271028.0374 | 330521.9968 | 188500 | 352336.4486 | 429678.5959 | 208800 | 390280.3738 | 475951.6754 | 232000 | 433644.8598 | 528835.1949 | 275500 | 514953.271 | 627991.7939
|  | #1 | 20 | 2.6667 | 0.53333 | 0.12275 | 100000 | 186915.8879 | 227946.2047 | 130000 | 242990.6542 | 296330.0661 | 144000 | 269158.8785 | 328242.5348 | 160000 | 299065.4206 | 364713.9275 | 190000 | 355140.1869 | 433097.7889
|  | #2 | 12 | 1.6 | 0.32 | 0.073648 | 60000 | 112149.5327 | 136767.7228 | 78000 | 145794.3925 | 177798.0397 | 86400 | 161495.3271 | 196945.5209 | 96000 | 179439.2523 | 218828.3565 | 114000 | 213084.1121 | 259858.6734
|  | NTH | 392 | 52.2667 | 10.4533 | 2.4058 | 1960000 | 3663551.402 | 4467745.612 | 2548000 | 4762616.822 | 5808069.296 | 2822400 | 5275514.019 | 6433553.681 | 3136000 | 5861682.243 | 7148392.979 | 3724000 | 6960747.664 | 8488716.663
|  | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 453 | 60.4 | 12.08 | 2.7802 | 2265000 | 4233644.86 | 5162981.536 | 2944500 | 5503738.318 | 6711875.997 | 3261600 | 6096448.598 | 7434693.412 | 3624000 | 6773831.776 | 8260770.458 | 4303500 | 8043925.234 | 9809664.919
| Vendure / NextJS MIN | MVP | 47 | 6.2667 | 1.2533 | 0.28845 | 235000 | 439252.3364 | 535673.581 | 305500 | 571028.0374 | 696375.6553 | 338400 | 632523.3645 | 771369.9567 | 376000 | 702803.7383 | 857077.7297 | 446500 | 834579.4393 | 1017779.804
|  | #1 | 20 | 2.6667 | 0.53333 | 0.12275 | 100000 | 186915.8879 | 227946.2047 | 130000 | 242990.6542 | 296330.0661 | 144000 | 269158.8785 | 328242.5348 | 160000 | 299065.4206 | 364713.9275 | 190000 | 355140.1869 | 433097.7889
|  | #2 | 19 | 2.5333 | 0.50667 | 0.11661 | 95000 | 177570.0935 | 216548.8945 | 123500 | 230841.1215 | 281513.5628 | 136800 | 255700.9346 | 311830.408 | 152000 | 284112.1495 | 346478.2311 | 180500 | 337383.1776 | 411442.8995
|  | NTH | 440 | 58.6667 | 11.7333 | 2.7004 | 2200000 | 4112149.533 | 5014816.503 | 2860000 | 5345794.393 | 6519261.454 | 3168000 | 5921495.327 | 7221335.765 | 3520000 | 6579439.252 | 8023706.405 | 4180000 | 7813084.112 | 9528151.356
|  | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 526 | 70.1333 | 14.0267 | 3.2282 | 2630000 | 4915887.85 | 5994985.183 | 3419000 | 6390654.206 | 7793480.739 | 3787200 | 7078878.505 | 8632778.664 | 4208000 | 7865420.561 | 9591976.294 | 4997000 | 9340186.916 | 11390471.85
ESTIMATED | Magento2 / Hyva MAX | MVP | 58 | 7.7333 | 1.5467 | 0.35596 | 290000 | 542056.0748 | 661043.9936 | 377000 | 704672.8972 | 859357.1917 | 417600 | 780560.7477 | 951903.3508 | 464000 | 867289.7196 | 1057670.39 | 551000 | 1029906.542 | 1255983.588
|  | #1 | 36 | 4.8 | 0.96 | 0.22094 | 180000 | 336448.5981 | 410303.1685 | 234000 | 437383.1776 | 533394.119 | 259200 | 484485.9813 | 590836.5626 | 288000 | 538317.757 | 656485.0695 | 342000 | 639252.3364 | 779576.0201
|  | #2 | 25 | 3.3333 | 0.66667 | 0.15343 | 125000 | 233644.8598 | 284932.7559 | 162500 | 303738.3178 | 370412.5826 | 180000 | 336448.5981 | 410303.1685 | 200000 | 373831.7757 | 455892.4094 | 237500 | 443925.2336 | 541372.2362
|  | NTH | 733 | 97.7333 | 19.5467 | 4.4987 | 3665000 | 6850467.29 | 8354228.402 | 4764500 | 8905607.477 | 10860496.92 | 5277600 | 9864672.897 | 12030088.9 | 5864000 | 10960747.66 | 13366765.44 | 6963500 | 13015887.85 | 15873033.96
|  | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 852 | 113.6 | 22.72 | 5.229 | 4260000 | 7962616.822 | 9710508.32 | 5538000 | 10351401.87 | 12623660.82 | 6134400 | 11466168.22 | 13983131.98 | 6816000 | 12740186.92 | 15536813.31 | 8094000 | 15128971.96 | 18449965.81
| Vendure / NextJS MAX | MVP | 89 | 11.8667 | 2.3733 | 0.54622 | 445000 | 831775.7009 | 1014360.611 | 578500 | 1081308.411 | 1318668.794 | 640800 | 1197757.009 | 1460679.28 | 712000 | 1330841.121 | 1622976.977 | 845500 | 1580373.832 | 1927285.161
|  | #1 | 36 | 4.8 | 0.96 | 0.22094 | 180000 | 336448.5981 | 410303.1685 | 234000 | 437383.1776 | 533394.119 | 259200 | 484485.9813 | 590836.5626 | 288000 | 538317.757 | 656485.0695 | 342000 | 639252.3364 | 779576.0201
|  | #2 | 40 | 5.3333 | 1.0667 | 0.24549 | 200000 | 373831.7757 | 455892.4094 | 260000 | 485981.3084 | 592660.1322 | 288000 | 538317.757 | 656485.0695 | 320000 | 598130.8411 | 729427.855 | 380000 | 710280.3738 | 866195.5778
|  | NTH | 770 | 102.6667 | 20.5333 | 4.7257 | 3850000 | 7196261.682 | 8775928.881 | 5005000 | 9355140.187 | 11408707.55 | 5544000 | 10362616.82 | 12637337.59 | 6160000 | 11514018.69 | 14041486.21 | 7315000 | 13672897.2 | 16674264.87
|  | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 935 | 124.6667 | 24.9333 | 5.7384 | 4675000 | 8738317.757 | 10656485.07 | 6077500 | 11359813.08 | 13853430.59 | 6732000 | 12583177.57 | 15345338.5 | 7480000 | 13981308.41 | 17050376.11 | 8882500 | 16602803.74 | 20247321.63

## Quote Mine B
Planning |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | MVP | MVP | Month | MVP | MVP | Month
|  | Min | Max | Min | Max |  | 391 | 714 | 4.382 | 414 | 705 | 4.3268
SUMS | MVP | 25 | 35 | 25 | 35 |  | #1 | #1 |  | #1 | #1
| #1 | 0 | 0 | 0 | 0 |  | 29 | 58 | 0.35596 | 47 | 89 | 0.54622
| #2 | 0 | 0 | 0 | 0 |  | #2 | #2 |  | #2 | #2
| TBD | 0 | 0 | 0 | 0 |  | 20 | 36 | 0.22094 | 20 | 36 | 0.22094
| Total | 25 | 35 | 25 | 35 |  | TBD | TBD |  | TBD | TBD
[7 empty] | 12 | 25 | 0.15343 | 19 | 40 | 0.24549
Hosting |  | Magento2 / Hyva |  | Vendure / NextJS
|  | Min | Max | Min | Max
SUMS | MVP | 52 | 114 | 32 | 64
| #1 | 0 | 0 | 0 | 0 | [6 empty] | költs. | 10384.216 |  |  | 13499.4808 |  |  | 15057.1132 |  |  | 16614.7456 |  |  | 19730.0104
| #2 | 0 | 0 | 0 | 0 |  |  | BSS Percent |  | 10% |  | bruttó | 9345.7944 |  |  | 12149.5327 |  |  | 13551.4019 |  |  | 14953.271 |  |  | 17757.0094
| TBD | 0 | 0 | 0 | 0 |  |  | Jarulekok |  | 53.5% |  | nettó | 5000 | 53.5% | 10% | 6500 | 53.5% | 10% | 7250 | 53.5% | 10% | 8000 | 53.5% | 10% | 9500 | 53.5% | 10%
| Total | 52 | 114 | 32 | 64 |  |  |  | HOURS | DAYS | WEEKS | MONTHS | 814687.5 | 1522780.374 | 1691978.193 | 1059093.75 | 1979614.486 | 2199571.651 | 1181296.875 | 2208031.542 | 2453368.38 | 1303500 | 2436448.598 | 2707165.109 | 1547906.25 | 2893282.71 | 3214758.567
[6 empty] | ESTIMATED | Vendure / NextJS MIN | MVP | 391 | 52.1333 | 10.4267 | 2.3997 | 1955000 | 3654205.607 | 4060228.453 | 2541500 | 4750467.29 | 5278296.989 | 2834750 | 5298598.131 | 5887331.256 | 3128000 | 5846728.972 | 6496365.524 | 3714500 | 6942990.654 | 7714434.06
[8 empty] | #1 | 29 | 3.8667 | 0.77333 | 0.17798 | 145000 | 271028.0374 | 301142.2638 | 188500 | 352336.4486 | 391484.9429 | 210250 | 392990.6542 | 436656.2825 | 232000 | 433644.8598 | 481827.622 | 275500 | 514953.271 | 572170.3011
Admin Site |  | Magento2 / Hyva |  | Vendure / NextJS |  |  |  | #2 | 20 | 2.6667 | 0.53333 | 0.12275 | 100000 | 186915.8879 | 207684.3198 | 130000 | 242990.6542 | 269989.6158 | 145000 | 271028.0374 | 301142.2638 | 160000 | 299065.4206 | 332294.9117 | 190000 | 355140.1869 | 394600.2077
|  | Min | Max | Min | Max |  |  | TBD | 12 | 1.6 | 0.32 | 0.073648 | 60000 | 112149.5327 | 124610.5919 | 78000 | 145794.3925 | 161993.7695 | 87000 | 162616.8224 | 180685.3583 | 96000 | 179439.2523 | 199376.947 | 114000 | 213084.1121 | 236760.1246
SUMS | MVP | 146 | 264 | 171 | 299 |  |  | Total | 452 | 60.2667 | 12.0533 | 2.7741 | 2260000 | 4224299.065 | 4693665.628 | 2938000 | 5491588.785 | 6101765.317 | 3277000 | 6125233.645 | 6805815.161 | 3616000 | 6758878.505 | 7509865.005 | 4294000 | 8026168.224 | 8917964.694
| #1 | 21 | 39 | 27 | 50 |  | Vendure / NextJS MAX | MVP | 705 | 94 | 18.8 | 4.3268 | 3525000 | 6588785.047 | 7320872.274 | 4582500 | 8565420.561 | 9517133.956 | 5111250 | 9553738.318 | 10615264.8 | 5640000 | 10542056.07 | 11713395.64 | 6697500 | 12518691.59 | 13909657.32
| #2 | 10 | 16 | 10 | 16 |  |  | #1 | 89 | 11.8667 | 2.3733 | 0.54622 | 445000 | 831775.7009 | 924195.2233 | 578500 | 1081308.411 | 1201453.79 | 645250 | 1206074.766 | 1340083.074 | 712000 | 1330841.121 | 1478712.357 | 845500 | 1580373.832 | 1755970.924
| TBD | 12 | 25 | 19 | 40 |  |  | #2 | 36 | 4.8 | 0.96 | 0.22094 | 180000 | 336448.5981 | 373831.7757 | 234000 | 437383.1776 | 485981.3084 | 261000 | 487850.4673 | 542056.0748 | 288000 | 538317.757 | 598130.8411 | 342000 | 639252.3364 | 710280.3738
| Total | 189 | 344 | 227 | 405 |  |  | TBD | 40 | 5.3333 | 1.0667 | 0.24549 | 200000 | 373831.7757 | 415368.6397 | 260000 | 485981.3084 | 539979.2316 | 290000 | 542056.0748 | 602284.5275 | 320000 | 598130.8411 | 664589.8235 | 380000 | 710280.3738 | 789200.4154
[8 empty] | Total | 870 | 116 | 23.2 | 5.3395 | 4350000 | 8130841.121 | 9034267.913 | 5655000 | 10570093.46 | 11744548.29 | 6307500 | 11789719.63 | 13099688.47 | 6960000 | 13009345.79 | 14454828.66 | 8265000 | 15448598.13 | 17165109.03
Public Site |  | Magento2 / Hyva |  | Vendure / NextJS
|  | Min | Max | Min | Max
SUMS | MVP | 108 | 201 | 126 | 207
| #1 | 8 | 19 | 20 | 39
| #2 | 10 | 20 | 10 | 20
| TBD | 0 | 0 | 0 | 0
| Total | 126 | 240 | 156 | 266
UI |  | Magento2 / Hyva |  | Vendure / NextJS
|  | Min | Max | Min | Max
SUMS | MVP | 60 | 100 | 60 | 100
| #1 | 0 | 0 | 0 | 0
| #2 | 0 | 0 | 0 | 0
| TBD | 0 | 0 | 0 | 0
| Total | 60 | 100 | 60 | 100
ESTIMATED | HOURS | 452 | 833 | 500 | 870
| DAYS | 60.2667 | 111.0667 | 66.6667 | 116
| WEEKS | 12.0533 | 22.2133 | 13.3333 | 23.2
| MONTHS | 2.7741 | 5.1124 | 3.0687 | 5.3395

## Quote DEV
[11 empty] | Phase | Magento2 / Hyva |  | Vendure / NextJS |  | Comments | Questions
[6 empty] | Planning |  |  |  |  | MVP | Hours Min Max |  | Hours Min Max
Planning |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | Planning |  |  |  | MVP | 25 | 35 | 25 | 35 | Planning, meetings etc.
|  | Min | Max | Min | Max
SUMS | MVP | 25 | 35 | 25 | 35
| #1 | 0 | 0 | 0 | 0
| #2 | 0 | 0 | 0 | 0
| TBD | 0 | 0 | 0 | 0
| Total | 25 | 35 | 25 | 35
[6 empty] | Hosting |  |  |  |  | MVP | Hours Min Max |  | Hours Min Max
Hosting |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | Database |  |  |  | MVP | 10 | 30 | 10 | 30 | Relational DB
|  | Min | Max | Min | Max |  | Application |  |  |  | MVP |  |  |  |  | 118k active users / 105k new users / 3m 11s AVG engagement time / 15k max concurrent
SUMS | MVP | 52 | 114 | 32 | 64 |  |  | CI/CD |  |  | MVP | 40 | 80 | 20 | 30
| #1 | 0 | 0 | 0 | 0 |  |  | Testing, Staging |  |  | MVP
| #2 | 0 | 0 | 0 | 0 |  | Vimeo |  |  |  | MVP
| TBD | 0 | 0 | 0 | 0 |  | Monitoring |  |  |  | MVP | 1 | 2 | 1 | 2 | CloudWatch / New Relic
| Total | 52 | 114 | 32 | 64 |  | Security |  |  |  | MVP | 1 | 2 | 1 | 2 | European CDN
[7 empty] | Monthly costs |  |  |  |  | ~$1200-$3500 |  | ~$800-$2500 |  | This also includes scaling with the capability to handle 2 times as many user than 2025.
[6 empty] | Admin Site |  |  |  |  | MVP | Hours Min Max |  | Hours Min Max
Admin Site |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | Product Management |  |  |  | MVP
|  | Min | Max | Min | Max |  |  | Products |  |  | MVP
SUMS | MVP | 146 | 264 | 171 | 299 |  |  |  | Grid |  | MVP | 1 | 2 | 2 | 4
| #1 | 21 | 39 | 27 | 50 |  |  |  | Bulk Actions |  | MVP | 1 | 2 | 2 | 3
| #2 | 10 | 16 | 10 | 16 |  |  |  | Add / Edit / Remove |  | MVP | 2 | 4 | 2 | 4
| TBD | 12 | 25 | 19 | 40 |  |  |  | Attributes |  | MVP | 4 | 8 | 4 | 8
| Total | 189 | 344 | 227 | 405 |  |  |  | Types |  | MVP | 4 | 8 | 4 | 8
[8 empty] | Catalogue |  |  | MVP
[9 empty] | Categories GTM |  | MVP | 6 | 10 | 6 | 8
[9 empty] | Variants |  | MVP | 4 | 8 | 10 | 15
[9 empty] | Inventory |  | MVP | 4 | 8 | 8 | 14
[9 empty] | Images / Media |  | MVP | 3 | 6 | 3 | 6
[9 empty] | Upsell |  | #1 | 2 | 4 | 3 | 5
[8 empty] | BISA Specific |  |  | MVP
[9 empty] | Gamify Points |  | MVP | 2 | 4 | 2 | 4
[9 empty] | Video Links |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Subscriptioned Price |  | MVP | 3 | 6 | 5 | 12
[9 empty] | Permissions |  | N/A | 2 | 4 | 5 | 10
[8 empty] | Events |  |  | N/A
[9 empty] | Grid |  | N/A | 0 | 0 | 0 | 0 |  | Events are not going to be differentiated from products
[9 empty] | Add / Edit / Remove |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Bookings |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Recurring Events |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Attendees |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Gamify Integration |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Calendar View |  | N/A | 0 | 0 | 0 | 0
[8 empty] | Videos |  |  | MVP
[9 empty] | Grid - Library |  | MVP | 2 | 4 | 2 | 5
[9 empty] | Add / Edit / Remove |  | MVP | 4 | 8 | 4 | 8
[9 empty] | DRM / Access Control |  | MVP | 6 | 12 | 12 | 20 | Digital Rights Management
[9 empty] | Progress Tracking |  | MVP | 10 | 15 | 10 | 15
[9 empty] | Playlists / Series |  | MVP | 10 | 15 | 10 | 15
[9 empty] | Subscription Mapping |  | MVP | 15 | 20 | 8 | 10
[9 empty] | Analytics |  | MVP | 4 | 8 | 8 | 15
[9 empty] | Gamify Badges |  | #1 | 5 | 10 | 10 | 20
[7 empty] | Order Fulfillment |  |  |  | MVP
[8 empty] | Orders |  |  | MVP
[9 empty] | Grid |  | MVP | 3 | 6 | 2 | 4
[9 empty] | Add / Edit / Remove |  | MVP | 3 | 6 | 2 | 3
[9 empty] | Status |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Bulk |  | N/A | 0 | 0 | 0 | 0
[9 empty] | Invoice |  | MVP
[10 empty] | Szamlazz.hu | MVP | 6 | 10 | 6 | 10
[8 empty] | Shipping |  |  | MVP
[9 empty] | Carrier |  | MVP
[10 empty] | Foxpost | MVP | 2 | 2 | 2 | 2
[10 empty] | DPD | MVP | 2 | 3 | 2 | 3
[10 empty] | MPL | MVP | 2 | 4 | 2 | 4
[9 empty] | Packing Slips |  | TBD
[10 empty] | PDF Labels | TBD | 1 | 3 | 3 | 5
[10 empty] | Shipping lists | TBD | 2 | 4 | 2 | 5
[9 empty] | Tracking |  | TBD | 3 | 6 | 8 | 15
[9 empty] | Returns |  | TBD | 6 | 12 | 6 | 15
[8 empty] | Payments / Refunds |  |  | MVP
[9 empty] | Refunds |  | TBD | 0 | 0 | 0 | 0
[9 empty] | Failed Payment Retry |  | #1 | 8 | 15 | 8 | 15
[9 empty] | Subscriptions |  | MVP | 6 | 12 | 6 | 12 |  | Talan ezt ki lehetne emelni mint kulon fejlesztesi egyseg
[7 empty] | Notifications |  |  |  | MVP
[8 empty] | Fulfillment reports |  |  | MVP | 3 | 6 | 5 | 6
[8 empty] | Stock alerts |  |  | MVP | 1 | 1 | 2 | 4
[8 empty] | Shipment notifications |  |  | MVP | 1 | 2 | 1 | 3
[7 empty] | User Management |  |  |  | MVP
[8 empty] | Add/Edit/Delete |  |  | MVP | 5 | 10 | 5 | 10
[8 empty] | User impersonation |  |  | MVP | 4 | 8 | 6 | 10
[7 empty] | CRM/Emails |  |  |  | MVP | 0 | 0 | 0 | 0
[7 empty] | Gamification |  |  |  | MVP
[8 empty] | Triggers |  |  | MVP
[9 empty] | Profile |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Purchase |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Subscription |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Video |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Event |  | MVP | 1 | 2 | 1 | 2
[9 empty] | Streak |  | MVP | 1 | 2 | 1 | 2
[8 empty] | Rewards / Badges |  |  | #1
[9 empty] | Grid - Library |  | #1 | 1 | 2 | 1 | 2
[9 empty] | Add / Edit / Remove / Upload |  | #1 | 5 | 8 | 5 | 8
[9 empty] | Discount? |  | #2 | 5 | 8 | 5 | 8
[9 empty] | Benefit? |  | #2 | 5 | 8 | 5 | 8
[7 empty] | Payment Integrations |  |  |  | MVP
[8 empty] | Stripe |  |  | MVP | 5 | 10 | 10 | 18
[8 empty] | Barion |  |  | N/A | 0 | 0 | 0 | 0
[8 empty] | SimplePay |  |  | N/A | 0 | 0 | 0 | 0
[7 empty] | Admin Users |  |  |  | MVP
[8 empty] | Add/Edit/Delete |  |  | MVP | 10 | 20 | 10 | 20
[8 empty] | Permissions |  |  | N/A | 0 | 0 | 0 | 0
[7 empty] | Metrics |  |  |  | N/A
[8 empty] | CRM / EMail |  |  | MVP | 0 | 0 | 0 | 0 |  | CRM GA4 etc can only cover most of these but custom function development is inevitable
[8 empty] | Conversion Rate |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | Micro-Funnels/Drop-offs |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | Orders Count |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | AOV / Items per Order |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | Traffic / Acquisition |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | Subscription Health |  |  | #1 | 0 | 0 | 0 | 0
[8 empty] | Gamification |  |  | #1 | 0 | 0 | 0 | 0
[8 empty] | Video Engagement |  |  | #1 | 0 | 0 | 0 | 0
[8 empty] | Retention |  |  | #2 | 0 | 0 | 0 | 0
[8 empty] | Site Performance |  |  | #2 | 0 | 0 | 0 | 0
[6 empty] | Public Site | [5 empty] | Hours Min Max |  | Hours Min Max
Public Site |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | PWA |  |  |  | MVP | 0 | 0 | 5 | 8 | progressive web application
|  | Min | Max | Min | Max |  | Miscellaneous |  |  |  | MVP
SUMS | MVP | 108 | 201 | 126 | 207 |  |  | Blog |  |  | MVP | 12 | 24 | 10 | 18 | headless cms
| #1 | 8 | 19 | 20 | 39 |  |  | Introduction |  |  | MVP | 2 | 3 | 2 | 3 | headless cms
| #2 | 10 | 20 | 10 | 20 |  |  | Carousel |  |  | MVP | 2 | 3 | 2 | 3 | headless cms
| TBD | 0 | 0 | 0 | 0 |  |  | FAQ |  |  | MVP | 2 | 3 | 2 | 3 | headless cms
| Total | 126 | 240 | 156 | 266 |  |  | Contact |  |  | MVP | 2 | 3 | 2 | 3 | headless cms
[8 empty] | Privacy & Compliance |  |  | MVP | 1 | 2 | 1 | 2 | e.g.GDPR, Cookie, Terms etc
[7 empty] | User |  |  |  | MVP
[8 empty] | Authentication |  |  | MVP | 1 | 2 | 4 | 6
[9 empty] | User impersonation |  | MVP | 1 | 3 | 1 | 4
[9 empty] | Social logins |  | MVP
[10 empty] | email + pw | MVP | 1 | 3 | 0 | 0
[10 empty] | apple | MVP | 3 | 8 | 8 | 10
[10 empty] | google | MVP | 2 | 6 | 8 | 10
[10 empty] | facebook | #1 | 1 | 1 | 1 | 1
[10 empty] | instagram | #1 | 1 | 3 | 6 | 12
[10 empty] | facebook | #1 | 2 | 5 | 6 | 12
[10 empty] | tiktok | #1 | 3 | 8 | 6 | 12
[10 empty] | QR Tv | #2 | 10 | 20 | 10 | 20
[8 empty] | Profile |  |  | MVP | 5 | 10 | 3 | 8
[8 empty] | Onboarding |  |  | MVP | 5 | 6 | 5 | 6 | structured profile setup flow
[8 empty] | Badges |  |  | #1 | 1 | 2 | 1 | 2
[8 empty] | Subscription |  |  | MVP | 14 | 20 | 12 | 18
[7 empty] | Catalog |  |  |  | MVP
[8 empty] | Products (including events) |  |  | MVP | 10 | 25 | 10 | 25
[8 empty] | Videos |  |  | MVP | 10 | 12 | 8 | 10
[7 empty] | Checkout |  |  |  | MVP
[8 empty] | Cart |  |  | MVP | 8 | 15 | 12 | 18
[8 empty] | Guest |  |  | MVP | 10 | 20 | 15 | 20
[8 empty] | Payment |  |  | MVP | 5 | 10 | 5 | 10
[8 empty] | Coupon code |  |  | MVP | 2 | 6 | 1 | 5
[8 empty] | Shipping |  |  | MVP | 2 | 5 | 2 | 5
[7 empty] | Video Player |  |  |  | MVP
[8 empty] | Embed |  |  | MVP | 2 | 4 | 2 | 4
[8 empty] | Progress Tracking |  |  | MVP | 2 | 2 | 2 | 2
[7 empty] | Gamification |  |  |  | MVP
[8 empty] | Triggers |  |  | MVP | 1 | 2 | 1 | 2
[8 empty] | Rewards |  |  | MVP | 3 | 4 | 3 | 4
[7 empty] | SEO |  |  |  | MVP
[8 empty] | server side rendering |  |  | MVP | 0 | 0 | 0 | 0
[8 empty] | search engine optimization |  |  | MVP | 0 | 0 | 0 | 0
[7 empty] | AI |  |  |  | #4
[8 empty] | Knowledge Base |  |  | #2 | 10 | 20 | 10 | 20
[6 empty] | UI | [5 empty] | Hours Min Max |  | Hours Min Max
UI |  | Magento2 / Hyva |  | Vendure / NextJS |  |  | Public FrontEnd |  |  |  | MVP | 60 | 100 | 60 | 100
|  | Min | Max | Min | Max
SUMS | MVP | 60 | 100 | 60 | 100
| #1 | 0 | 0 | 0 | 0
| #2 | 0 | 0 | 0 | 0
| TBD | 0 | 0 | 0 | 0
| Total | 60 | 100 | 60 | 100
[6 empty] | Maintenance | [5 empty] | Hours Min Max |  | Hours Min Max
[6 empty] | Future ideas | [5 empty] | Hours Min Max |  | Hours Min Max